## Sheet1
Week | Day | Date | Recurring Tasks | Team Goals | Individual Deliverables
[5 empty] | Ben | Victor | Nick | Jacob | Dylan | Zeming
1 | S | 2021-03-28
| M | 2021-03-29 | 1000 Team Meeting
| T | 2021-03-30
| W | 2021-03-31
| Th | 2021-04-01 | 1000 Sponser Meeting
| F | 2021-04-02 | Progress Report
| S | 2021-04-03
2 | S | 2021-04-04
| M | 2021-04-05 | 1000 Team Meeting
| T | 2021-04-06
| W | 2021-04-07 |  | Finish Blimp Design Document and send to sponsor | Assist with writting Metrics | Write Software chapter introduction, Review Design Space chapter | Draft outline for Introduction section for the FOCUS document |  |  | Select some of the originals you need in your design
| Th | 2021-04-08 | 1000 Sponser Meeting | Discuss Blimp Design document with Sponsor | Review Metrics section with Jacob and format information into new doc | Write Software chapter introduction, Review Design Space chapter |  | Write Chapter 3: Metrics | Finish comments for Dr.Faust
| F | 2021-04-09 | Progress Report | Revise Blimp Design Document, Review Metrics section from previous doc, Begin Project Wiki | Decide Best software, Review chapter details | Decide Best Software, write detailed summary | Decide Best Software, write detailed summary | Decide Best Software, write detailed summary | Review the Design Space section of the document, Introduction Rough Draft | Review the Design Space section of the document, Introduction Rough Draft
| S | 2021-04-10 |  | Revise Blimp Design Document | Read AA 449 Final Milestone Report Blimp Project | Write detailed summary of chosen software | Write detailed summary of chosen software | Write detailed summary of chosen software | Edit the Introduction section and continue to add to it, Look at annotated Bib. due to Dr. Faust comments | Write Blimp Performance Characteristics
3 | S | 2021-04-11 |  | Revise Blimp Design Document | Read AA 449 Final Milestone Report Blimp Project | Write detailed summary of chosen software | Write detailed summary of chosen software | Write detailed summary of chosen software | Design a dynamic equations model document (Engineering Analysis), Come up with presentation matter for Annotated Bib. | Write Chapter 3: Metrics
| M | 2021-04-12 | 0900 Team Meeting | Revise Blimp Design Document to final draft and send to sponsor | Impliment suggestions/corrections from Mark | Write detailed summary of chosen software | Write detailed summary of chosen software | Write detailed summary of chosen software | Finish a dynamic equation documentation for the simulation team and for report | Write Chapter 3: Metrics
| T | 2021-04-13 |  |  | Impliment suggestions/corrections from Mark |  |  |  | Refine the Introduction section and start to implement a "storyline" to blimps looking at Dr.Per contri. | Learn mathematics about airship design
| W | 2021-04-14 |  |  | Research methods of testing blimp for Ch 3 | achieve stationary blimp simulation | achieve stationary blimp simulation | achieve stationary blimp simulation | Assist in the writing in metrics, performance, design space, start reading Dr. P +65 paper. | Read different reports to check for required originals
| Th | 2021-04-15 | 1000 Team Meeting |  | Create a rough test for simulation for Ch 3 | Add control surfaces | Add control surfaces | Add control surfaces | Start to create a journal presentation to present to the other team members, as not all have read the papers | Perfect the information that needs to be perfected in document
| F | 2021-04-16 | Progress Report |  | Review Ch 4 metrics table with Team | control propellers with exteral code | control propellers with exteral code | control propellers with exteral code | Finish +65 paper from Dr. Per. | Read the completed report
| S | 2021-04-17 |  |  | Read into simulation/ get a debrief from the simulation team on simulations
4 | S | 2021-04-18 | [6 empty] | Create comprehensive dynamic modeling equations of blimp
| M | 2021-04-19 | 0900 Team Meeting | Achieve basic blimp simulation | Finalize tesing | Achieve Controled flight with code | Achieve Controled flight with code | Achieve Controled flight with code | Start second +80 paper from Dr. Per
| T | 2021-04-20 |  |  | Assist with prototype gondola design | Refine Controled flight | Refine Controled flight | Refine Controled flight | Start Prototype design (Gondola)
| W | 2021-04-21 |  |  | Assist Prototype Design: Thrusters | prepare simulation for sponsor presentation | prepare simulation for sponsor presentation | prepare simulation for sponsor presentation | Prototype Design: Thrusters
| Th | 2021-04-22 | 1000 Sponser Meeting | Present basic blimp simulation to sponsor | Assist Prototype Design: Thrusters | Present basic simulation to sponsor | Present basic simulation to sponsor | Present basic simulation to sponsor | Prototype Design: Thrusters
| F | 2021-04-23 | Progress Report |  | Assist Prototype Design: Cage | Review lessons from simulation creation and sponsor input | Review lessons from simulation creation and sponsor input | Review lessons from simulation creation and sponsor input | Prototype Design: Cage
| S | 2021-04-24 | [6 empty] | Finish second +80 Paper from Dr. P
5 | S | 2021-04-25 |  |  | Prototype Design: Cage |  |  |  | Prototype Design: Cage
| M | 2021-04-26 | 0900 Team Meeting |  | Prototype Design: Cage door | integrate metrics measurement | integrate metrics measurement | integrate metrics measurement | Prototype Design: Cage door
| T | 2021-04-27 |  |  | Prototype Design: Cage door | integrate metrics measurement | integrate metrics measurement | integrate metrics measurement | Prototype Design: Cage door
| W | 2021-04-28 |  |  | Prototype Design: Envelope Attachment | integrate metrics measurement | integrate metrics measurement | integrate metrics measurement | Prototype Design: Envelope Attachment
| Th | 2021-04-29 | 1000 Sponser Meeting | Refine blimp simulation, add movement and plan for sponsor to add autonomy | Prototype Design: Envelope Attachment | Communicate metrics measurement with sponsor and make changes based on input | Communicate metrics measurement with sponsor and make changes based on input | Communicate metrics measurement with sponsor and make changes based on input | Prototype Design: Envelope Attachment
| F | 2021-04-30 | Progress Report |  | Design iteration: With Dylan | integrate metrics measurement | integrate metrics measurement | integrate metrics measurement | Design iteration: With Ben
| S | 2021-05-01 |  |  | Design iteration: With Dylan |  |  |  | Design iteration: With Ben
6 | S | 2021-05-02 |  |  | Design iteration: With Dylan |  |  |  | Design iteration: With Ben
| M | 2021-05-03 | 0900 Team Meeting |  | Design Choice (Grams per design calculation) | set up flight path simulation demonstration | set up flight path simulation demonstration | set up flight path simulation demonstration | Design Choice (Grams per design calculation)
| T | 2021-05-04 |  |  | Design Choise (Best component ranking) | set up flight path simulation demonstration | set up flight path simulation demonstration | set up flight path simulation demonstration | Design Choise (Best component ranking)
| W | 2021-05-05 |  | Begin working on Capstone presentation | Prepare for Presentation | polish final blimp simulation for sponsor | polish final blimp simulation for sponsor | polish final blimp simulation for sponsor | Prepare for Presentation
| Th | 2021-05-06 | 1000 Sponser Meeting | Present final simulation to sponsor (sponsor handoff?) | Present Physical Blimp Airframe Design | Present Blimp Simulation | Present Blimp Simulation | Present Blimp Simulation | Present Physical Blimp Airframe Design
| F | 2021-05-07 | Progress Report |  | Reflect on Project Deliverables in silence | Reflect on Project Deliverables in silence | Reflect on Project Deliverables in silence | Reflect on Project Deliverables in silence | Reflect on Project Deliverables in silence | Reflect on Project Deliverables in silence
| S | 2021-05-08
7 | S | 2021-05-09
| M | 2021-05-10 | 0900 Team Meeting
| T | 2021-05-11
| W | 2021-05-12
| Th | 2021-05-13 | 1000 Sponser Meeting
| F | 2021-05-14 | Progress Report
| S | 2021-05-15
8 | S | 2021-05-16
| M | 2021-05-17 | 0900 Team Meeting
| T | 2021-05-18
| W | 2021-05-19
| Th | 2021-05-20 | 1000 Sponser Meeting
| F | 2021-05-21 | Progress Report
| S | 2021-05-22
9 | S | 2021-05-23
| M | 2021-05-24 | 0900 Team Meeting |  | Discus Slideshow presentation | Discus Slideshow presentation | Discus Slideshow presentation | Discus Slideshow presentation | Discus Slideshow presentation | Discus Slideshow presentation
| T | 2021-05-25 |  |  | prepare slideshow | prepare slideshow | prepare slideshow | prepare slideshow | prepare slideshow | prepare slideshow
| W | 2021-05-26 |  |  | prepare slideshow | prepare slideshow | prepare slideshow | prepare slideshow | prepare slideshow | prepare slideshow
| Th | 2021-05-27 | 1000 Sponser Meeting
| F | 2021-05-28 | Progress Report | Prepare Slideshow | prepare slideshow | prepare slideshow | prepare slideshow | prepare slideshow | prepare slideshow | prepare slideshow
| S | 2021-05-29
10 | S | 2021-05-30
| M | 2021-05-31 | 0900 Team Meeting
| T | 2021-06-01
| W | 2021-06-02
| Th | 2021-06-03 |  | Capstone Presentation & Report Due
| F | 2021-06-04
| S | 2021-06-05