## Sheet1
Week | Day | Date | Recurring Tasks | Team Goals | Individual Deliverables
[5 empty] | Ben | Victor | Nick | Jacob | Dylan | Zeming
1 | S | 2021-03-28
| M | 2021-03-29 | 1000 Team Meeting
| T | 2021-03-30
| W | 2021-03-31
| R | 2021-04-01 | 1000 Sponser Meeting
| F | 2021-04-02 | Progress Report
| S | 2021-04-03
2 | S | 2021-04-04
| M | 2021-04-05 | 1000 Team Meeting
| T | 2021-04-06
| W | 2021-04-07 |  | Finish Blimp Design Document and send to sponsor | Decide Best software, Review chapter details | Decide Best Software, write detailed summary | Decide Best Software, write detailed summary | Decide Best Software, write detailed summary | Draft outline for Introduction section for the FOCUS document
| R | 2021-04-08 | 1000 Sponser Meeting | Discuss Blimp Design document with Sponsor | Review Metrics section with Jacob and format information into new doc |  |  | Write Software chapter introduction, Review Design Space chapter | Finish comments for Dr.Faust
| F | 2021-04-09 | Progress Report | Revise Blimp Design Document, Review Metrics section from previous doc, Begin Project Wiki | Read AA 449 Final Milestone Report Blimp Project |  |  | Write Software chapter introduction, Review Design Space chapter | Review the Design Space section of the document, Introduction Rough Draft
| S | 2021-04-10 |  | Revise Blimp Design Document |  |  |  |  | Edit the Introduction section and continue to add to it, Look at annotated Bib. due to Dr. Faust comments
3 | S | 2021-04-11 |  | Revise Blimp Design Document |  |  |  |  | Design a dynamic equations model document (Engineering Analysis), Come up with presentation matter for Annotated Bib.
| M | 2021-04-12 | 0900 Team Meeting | Revise Blimp Design Document to final draft and send to sponsor | Assist with writting Metrics |  |  | Write Chapter 3: Metrics | Finish a dynamic equation documentation for the simulation team and for report
| T | 2021-04-13 |  |  | Assist with writting Metrics |  |  | Write Chapter 3: Metrics | Refine the Introduction section and start to implement a "storyline" to blimps looking at Dr.Per contri.
| W | 2021-04-14 |  |  |  | Learn software of choice | Learn software of choice | Learn software of choice | Assist in the writing in metrics, performance, design space, start reading Dr. P +65 paper.
| R | 2021-04-15 | 1000 Sponser Meeting |  |  | Learn software of choice | Learn software of choice | Learn software of choice | Start to create a journal presentation to present to the other team members, as not all have read the papers
| F | 2021-04-16 | Progress Report |  |  | produce model/simulation to present at moday team meeting | produce model/simulation to present at moday team meeting | produce model/simulation to present at moday team meeting | Finish +65 paper from Dr. Per.
| S | 2021-04-17 |  |  |  | produce model/simulation to present at moday team meeting | produce model/simulation to present at moday team meeting | Unavailable | Read into simulation/ get a debrief from the simulation team on simulations
4 | S | 2021-04-18 |  |  |  | produce model/simulation to present at moday team meeting | produce model/simulation to present at moday team meeting | produce model/simulation to present at moday team meeting | Create comprehensive dynamic modeling equations of blimp
| M | 2021-04-19 | 0900 Team Meeting | Achieve basic blimp simulation |  | Present software and abilities | Present software and abilities | Present software and abilities | Start second +80 paper from Dr. Per
| T | 2021-04-20 |  |  |  | polish blimp simulation | polish blimp simulation | polish blimp simulation
| W | 2021-04-21 |  |  |  | prepare simulation for sponsor presentation | prepare simulation for sponsor presentation | prepare simulation for sponsor presentation
| R | 2021-04-22 | 1000 Sponser Meeting | Present basic blimp simulation to sponsor
| F | 2021-04-23 | Progress Report
| S | 2021-04-24 | [6 empty] | Finish second +80 Paper from Dr. P
5 | S | 2021-04-25
| M | 2021-04-26 | 0900 Team Meeting
| T | 2021-04-27
| W | 2021-04-28
| R | 2021-04-29 | 1000 Sponser Meeting | Refine blimp simulation, add movement and plan for sponsor to add autonomy
| F | 2021-04-30 | Progress Report
| S | 2021-05-01
6 | S | 2021-05-02
| M | 2021-05-03 | 0900 Team Meeting
| T | 2021-05-04
| W | 2021-05-05 |  | Begin working on Capstone presentation | polish final blimp simulation for sponsor | polish final blimp simulation for sponsor | polish final blimp simulation for sponsor | polish final blimp simulation for sponsor | polish final blimp simulation for sponsor
| R | 2021-05-06 | 1000 Sponser Meeting | Present final simulation to sponsor
| F | 2021-05-07 | Progress Report
| S | 2021-05-08
7 | S | 2021-05-09
| M | 2021-05-10 | 0900 Team Meeting
| T | 2021-05-11
| W | 2021-05-12
| R | 2021-05-13 | 1000 Sponser Meeting
| F | 2021-05-14 | Progress Report
| S | 2021-05-15
8 | S | 2021-05-16
| M | 2021-05-17 | 0900 Team Meeting
| T | 2021-05-18
| W | 2021-05-19
| R | 2021-05-20 | 1000 Sponser Meeting
| F | 2021-05-21 | Progress Report
| S | 2021-05-22
9 | S | 2021-05-23
| M | 2021-05-24 | 0900 Team Meeting
| T | 2021-05-25
| W | 2021-05-26
| R | 2021-05-27 | 1000 Sponser Meeting
| F | 2021-05-28 | Progress Report
| S | 2021-05-29
10 | S | 2021-05-30
| M | 2021-05-31 | 0900 Team Meeting
| T | 2021-06-01
| W | 2021-06-02
| R | 2021-06-03 |  | Capstone Presentation
| F | 2021-06-04
| S | 2021-06-05